## Ark1
TASK NAME | START DATE | END DATE | DURATION (DAYS) | ESTIMATION (HOURS) | RESPONSIBLE
RESEARCH FOR MAIN LAYOUT | 2019-04-15 09:00 | 2019-04-19 | 5 | 37.5 | Project manager, graphic designer
Collect client´s vision & goal | 2019-04-15 09:00 | 2019-04-17 | 3 | 22.5 | Project manager
Request client moodboard | 2019-04-15 | 2019-04-15 | 1 | 7.5 | Project manager
Research competitor brands | 2019-04-16 | 2019-04-17 | 2 | 15 | Project manager
Present results of research to client | 2019-04-18 | 2019-04-19 | 2 | 15 | Visual designer and project manger
CONSEPT | 2019-04-22 | 2019-04-24 | 3 | 22.5 | Project manager, interaction designer and content specialist
Clarify brand strategy and positioning in the market | 2019-04-22 | 2019-04-23 | 2 | 15 | Project manager, interaction designer and content specialist
Client feedback | 2019-04-23 | 2019-04-23 | 1 | 7.5 | Project manager, interaction designer and content specialist
Draft a creativity brief | 2019-04-23 | 2019-04-23 | 1 | 7.5 | Project manager, interaction designer and content specialist
Gain client approval of creative brief | 2019-04-23 | 2019-04-24 | 2 | 15 | Project manager, interaction designer and content specialist
Consept approve | 2019-04-24 | 2019-04-24 | 1 | 7.5 | Project manager, interaction designer and content specialist
COLORS AND GRAPHICS | 2019-04-25 | 2019-05-01 | 5 | 37.5 | Project manager visual designer
Draft the page layout | 2019-04-25 | 2019-04-25 | 1 | 7.5 | Visual designer, interaction designer
Make color swatches | 2019-04-26 | 2019-04-29 | 4 | 30 | Visual designer
Design logo | 2019-04-26 | 2019-04-29 | 4 | 30 | Visual designer
Create icons | 2019-04-26 | 2019-04-29 | 4 | 30 | Visual designer
Gain client approval of colors and graphics | 2019-04-30 | 2019-05-01 | 2 | 15 | Visual designer, interaction designer
CONTENT PRESENTATION | 2019-04-25 | 2019-05-01 | 5 | 37.5 | Visual designer, interaction designer
Fonts | 2019-04-25 | 2019-04-25 | 1 | 7.5 | Visual designer, interaction designer
Font sizes, font colors | 2019-04-26 | 2019-04-29 | 4 | 30 | Visual designer, interaction designer
Photoshoot | 2019-04-26 | 2019-04-29 | 4 | 30 | Photographer
Write and text for the website | 2019-04-26 | 2019-04-29 | 4 | 30 | Copywriter/content specialist
Gain client approval of content and fonts | 2019-04-30 | 2019-05-01 | 2 | 15 | Content specialist, interaction designer
DEVELOPMENT | 2019-05-02 | 2019-05-08 | 5 | 37.5 | Front-end developer, interactions designer, content specialist & project manager
Download and add fonts and images | 2019-05-02 | 2019-05-02 | 1 | 7.5 | Front-end developer
Home page, header, main menu | 2019-05-02 | 2019-05-02 | 1 | 7.5 | Front-end developer
Set up the order form | 2019-05-03 | 2019-05-04 | 2 | 15 | Front-end developer
Footer | 2019-05-04 | 2019-05-04 | 1 | 7.5 | Front-end developer
Testing | 2019-05-05 | 2019-05-06 | 2 | 15 | Interaction designer, content specialist and project manager
Bug fix | 2019-05-06 | 2019-05-08 | 2 | 15 | Front-end developer
PRESENTATION | 2019-05-08 | 2019-05-10 | 3 | 22.5 | Project manager and content specialist
Make and prepare the presentation of the website | 2019-05-08 | 2019-05-09 | 2 | 15 | Project manager and content specialist
Presentation of the finish product | 2019-05-10 | 2019-05-10 | 1 | 7.5 | Project manager and content specialist

## Ark2
Project manager
Visual designer
Interaction designer
Content specialist/ copywriter
Photographer
Front-End developer

## Ark3
TASK NAME | DAYS SINCE START | DURATION (DAYS) | ESTIMATION (HOURS) | RESPONSIBLE
RESEARCH FOR MAIN LAYOUT | 0 | 5 | 37.5 | Project manager, graphic designer
Collect client´s vision & goal | 0 | 3 | 22.5 | Project manager
Request client moodboard | 0 | 1 | 7.5 | Project manager
Research competitor brands | 1 | 2 | 15 | Project manager
Present results of research to client | 3 | 2 | 15 | Visual designer and project manger
CONCEPT | 6 | 3 | 22.5 | Project manager, interaction designer and content specialist
Clarify brand strategy and positioning in the market | 6 | 2 | 15 | Project manager, interaction designer and content specialist
Client feedback | 7 | 1 | 7.5 | Project manager, interaction designer and content specialist
Draft a creativity brief | 7 | 1 | 7.5 | Project manager, interaction designer and content specialist
Gain client approval of creative brief | 7 | 2 | 15 | Project manager, interaction designer and content specialist
Consept approve | 8 | 1 | 7.5 | Project manager, interaction designer and content specialist
COLORS AND GRAPHICS | 9 | 5 | 37.5 | Project manager visual designer
Draft the page layout | 9 | 1 | 7.5 | Visual designer, interaction designer
Make color swatches | 10 | 4 | 30 | Visual designer
Design logo | 10 | 4 | 30 | Visual designer
Create icons | 10 | 4 | 30 | Visual designer
Gain client approval of colors and graphics | 14 | 2 | 15 | Visual designer, interaction designer
CONTENT PRESENTATION | 9 | 5 | 37.5 | Visual designer, interaction designer
Fonts | 9 | 1 | 7.5 | Visual designer, interaction designer
Font sizes, font colors | 10 | 4 | 30 | Visual designer, interaction designer
Photoshoot | 10 | 4 | 30 | Photographer
Write and text for the website | 10 | 4 | 30 | Copywriter/content specialist
Gain client approval of content and fonts | 14 | 2 | 15 | Content specialist, interaction designer
DEVELOPMENT | 16 | 5 | 37.5 | Front-end developer, interactions designer, content specialist & project manager
Download and add fonts and images | 16 | 1 | 7.5 | Front-end developer
Home page, header, main menu | 16 | 1 | 7.5 | Front-end developer
Set up the order form | 17 | 2 | 15 | Front-end developer
Footer | 18 | 1 | 7.5 | Front-end developer
Testing | 19 | 2 | 15 | Interaction designer, content specialist and project manager
Bug fix | 20 | 2 | 15 | Front-end developer
PRESENTATION | 22 | 3 | 22.5 | Project manager and content specialist
Make and prepare the presentation of the website | 22 | 2 | 15 | Project manager and content specialist
Presentation of the finish product | 24 | 1 | 7.5 | Project manager and content specialist